## Roles Distribution Data Base (hidden)
Programming
Graphic Arts
Animations
Sounds
UI / UX
Level Design
Management
Game Design

## Roles Distribution
Responsibility | Role | Development Area / Groups | Who | How
The kind of stuff we need to do for sure in a game project | Who normally do this kind of stuff on the industry | What is the macro development area responsible for this item? | Who on our team will be responsible for this item | How this item will be done, what tools will be used and if will be made by theirselves or by an AI assistant
Programming Planning | Programmer Lead | Programming | Renee Pollet | Unity and Visual Script |  | Anna Victoria
Code architecture | Programmer Archtect | Programming | Renee Pollet | Unity and Visual Script |  | Renee Pollet
Gameplay Programming | Gameplay Programmer | Programming | Renee Pollet | Unity and Visual Script |  | Daril Camilo
Graphic Programming | Graphic Proogrammer | Programming | Musse Hidru | Unity and Visual Script |  | Musse Hidru
Audio Programming | Audio Programmer | Programming | Renee Pollet | Unity and Visual Script |  | Tierra
AI Programming | AI Programmer | Programming | Musse Hidru | Unity and Visual Script |  | Autumn McClinchey
UI Programming | UI Programmer | Programming | Renee Pollet | Unity and Visual Script
Programming Tasks Validation | Programmer Lead | Programming | Daril Camilo | Unity, Monday.com
Make Character Assets | Technical Artist | Graphic Arts | Autumn McClinchey | Blender
Make Enemies Assets | Technical Artist | Graphic Arts | Anna Victoria | Blender
Make Bosses Assets | Technical Artist | Graphic Arts | Autumn McClinchey | Blender
Make the Environment Assets | Technical Artist | Graphic Arts | Autumn McClinchey | Aseprite
Make the animations | Animator | Animations | Autumn McClinchey | Aseprite
Make UI Assets | Technical Artist | Graphic Arts | Tierra | Aseprite
Design Tasks Validator | Game Designer | Game Design | Daril Camilo | Monday.com
Make Sounds Assets | Sounds Designer | Sounds | Daril Camilo | Audacity
Think the UI System | UI Designer | UI / UX | Musse Hidru | Aseprite and Pinterest
Think the Sound System | Sounds Designer | Sounds | Daril Camilo | freesfx.com, chosic.com and pixabay.com
Level Building | Level Designer | Level Design | Renee Pollet | Unity, Houdini
Think the Game Systems | Systems Designer | Level Design | Musse Hidru | Draw.io
Create the Itch page | Project Manager | Management | Daril Camilo | Itch.io and Adobe XD
Make the Level Design Document | Project Manager | Management | Daril Camilo | Canva
Manage the tasks | Project Manager | Management | Daril Camilo | Monday.com
Submit the game | Project Manager | Management | Daril Camilo | Itch.io
Create the Build | Project Manager | Management | Daril Camilo | Unity
Create the game narrative | Narrative Designer | Game Design | Daril Camilo | Microsoft Word and Pinterest
Write the game Lore | Writer | Game Design | Daril Camilo | Microsoft Word and Pinterest
QA Testing | QA Tester | Management | Daril Camilo | Unity
Group Members
Daril Camilo | Renee Pollet | Anna Victoria | Autumn McClinchey | Musse Hidru | Tierra
Management / Generalist | Programmer / Level Designer | Technical Artist | Artist Lead | Programmer / Level Designer | Technical Artist

## Priorization Standard
Priority Level | Criteria | How to deal with this task
Priority status registered in the task management tool. | What the project manager should consider to tag task priority. | How the developer should handle this task
Low | It is part of a set of important implementations for systems or levels not yet implemented in the game | They will be the last on your execution list.
Normal | It is part of the set of implementations related to the content that is currently being developed in the game, but it has an aesthetic character. | Ideally, all or most of the tasks on your list should have this priority level, this would demonstrate execution at the correct time.
High | It is linked to the content currently being developed in the game and directly affects the gameplay and the player's experience. | Put the other tasks on your list for later, if necessary, renegotiate the delivery deadline with the project manager and execute this one.
Urgent | It is generating bugs in the game, preventing gameplay from flowing normally or it is one of the last 3 tasks to finish the sprint. | Stop the execution of all your tasks and run this one. If necessary, request support from the team so that your other tasks do not accumulate.

## Monday Integration
Feature | Concept | Options | Example | Know more about
Person | Who is responsible to execute the task |  |  | Roles Distribution Standard
Groups | Are the departments responsible to deliver the task |  |  | Roles Distribution Standard
Status | In what stage of advancement the task are |  |  | Status Standard
Sprint | During what sprint the task should to be delivered to contribute to the final product the team needs to deliver in that milestone |  |  | Project Milestones
Data | Is the deadline for the task be delivered
Priority | It is essential to determine when the task need be started, every team member needs to read the priorization scale standard for organize his / her execution properly |  |  | Priorization Standard
Label | It is about what game's part will be impacted by the task |  |  | Label
Issue Type | Issue type it is a field we created to track the kind of problems we have more during the project. It needs to be selected if we have some bug or if the task delivered is not aproved during the validation phase. |  |  | Bugs and Issues solving

## Environment Layers Sequence (hidden)
Layer | CavernEnvironment | DeepCavernEnvironment | SunnyEnvironment | BorealEnvironment
1 | Foreground | Foreground | Foreground | Foreground
2 | White Filter | Background 1 | First Bushes | Blue Filter
3 | Background 1 | Filter | Blue Filter | Green Filter
4 | Background 2 | Background 2 | First Trees | First Bushes
5 | Background 3 | Coloured Screen | Ground 1 | First Trees
6 | Background 4 |  | Second Bushes | Ground 1
7 | Background 5 |  | Second Trees | Green Filter
8 | Background 6 |  | Ground 2 | Second Bushes
9 | Coloured Screen |  | Cloudys | Second Trees
10 |  |  | Coloured Screen | Ground 2
Green Filter
11 |  |  |  | Thirdth Bushes
12 |  |  |  | Thirdth Trees
13 |  |  |  | Ground 3
14 |  |  |  | Cloudys
15 |  |  |  | Coloures Screen
Player View

## WorkFlow Integration
Column | Sequence Order (Left to right) | What tasks should be here | Best Practice
To Do | 1 | Tasks you did not start to work in so far | Always look how many tasks you have and what are their deadlines and plan yourself to do everything on time
Doing | 2 | Tasks you are currently doing | every time you work in some task, post some report with the last advancements
In Test | 3 | Tasks you finish and are waiting for validation | Keep looking this tasks, if some of this ones back to doing, certainly will have there some report for you fix something
Done | 4 | Validated Tasks | Always work eficiently for deliver everything with some advancement to have enough time to fix something if be necessary
Project Standards | 5 | Documents and Standards to support our work | Always give a look on the documents related to your work

## Sound Table
Category / Folder | Sub Category / Sub Folder | Triggers | File Name | Transcription | Status | Quality Assurance Test | Transcription
UI Sounds | UI Sounds | When some button is clicked | ButtonClick |  | DONE
Environment Sounds | Environment Sounds | During the Gameplay | BackgroundSound |  | DONE
UI Sounds | UI Sounds | While the player has the main menu open | MainMenuBGSound |  | DONE |  |  | OK | Player Movement and Interactions | Environment Sounds | DONE
Gameplay Sounds | Player Movement and Interactions | When the player get some item | GettingCollectableItem |  | DONE |  |  | NOK | Enemy Actions | Gameplay Sounds | DOING
UI Sounds | UI Sounds | When the player Interact with some temple | AccessTemple |  | DONE |  |  |  | Boss Actions | UI Sounds | REMOVED
Gameplay Sounds | Player Movement and Interactions | When the player suffer some damage | GettingPhysicalHit |  | DONE |  |  |  | Player Spells |  | TO DO
Gameplay Sounds | Player Spells | When the player casts a Fire Projectile spell | FireProjectile |  | DONE |  |  |  | Environment Sounds
Gameplay Sounds | Player Spells | When the player casts a Ice Projectile spell | IceProjectile |  | DONE |  |  |  | UI Sounds
Gameplay Sounds | Player Spells | When the player casts a Lighting Projectile spell | LightiningProjectile |  | DONE |  |  |  | UI Dialogues
Environment Sounds | Environment Sounds | When the Witch is in the player's screen | WitchBGSound |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Frost Push spell | FrostPushSpell |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Ring of Fire spell | CastingRingOfFire |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Blizzard spell | BlizzardSpell |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Tesla Coil spell | TeslaCoilSpell |  | DONE | OK
Sounds | Player Spells | When the player casts the Ice Spike spell | IceSpikeSPell |  | DONE | OK
Sounds | Player Spells | When the player casts the Meteor spell | MeteorSpell |  | DONE
Sounds | Player Spells | When the player casts the Ice Machine spell | IceMachineSpell |  | DONE
Gameplay Sounds | Player Movement and Interactions | When the player Get Souls | GettingSouls |  | DONE
Gameplay Sounds | Player Movement and Interactions | When the player be damaged by some magical hit | MagicalHit |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Trail of Fire spell | TrailOfFireSpell |  | DONE | OK | the sound is doubling
Gameplay Sounds | Player Spells | When the player casts the Shotgun spell | ShotGunSpell |  | DONE
Gameplay Sounds | Player Spells | When the player casts the Burst Lightning spell | BurstLightningSpell |  | DONE | OK
Gameplay Sounds | Player Spells | When the player casts the Light Ball spell | LightBallSpell |  | DONE
Gameplay Sounds | Player Spells | When the Fire Projectile Hits some target | FireImpact |  | DONE
Gameplay Sounds | Player Spells | When the Fire Ice Hits some target | IceImpact |  | DONE
Gameplay Sounds | Player Spells | When the Fire Lightning Hits some target | LightningImpact |  | DONE
Gameplay Sounds | Player Spells | When the Meteor Collides with the ground | MeteorCollision |  | DONE
Gameplay Sounds | Enemy Actions | When the witch screaming animations is played | WitchScreaming |  | DONE
UI Sounds | UI Dialogues | When the player get a defense rune on the shop | MoreResilient |  | DONE |  | You will be more resilient now.
UI Sounds | UI Dialogues | When the player get a cooldown reduction on the shop | WillingToFight |  | DONE |  | Now you will be more willing to fight
UI Sounds | UI Dialogues | When the player get a souls boots on the shop | SoulsFromCreatures |  | DONE |  | Now you will be able to extract more souls from creatures
UI Sounds | UI Dialogues | When the player unblock the ultimate spell slot on the shop | UltimateSpells |  | DONE |  | Congratulations, now you can use the most powerful spells
UI Sounds | UI Dialogues | When the player change his base spell on the shop | NewBase |  | DONE |  | New base spell chosen
UI Sounds | UI Dialogues | When the player arrive with more souls on the shop | MoreSouls |  | DONE |  | Oh you arrived with more souls
UI Sounds | UI Dialogues | When the player reroll the special spell on the shop | SpellUpdated |  | DONE |  | Spell Updated!
UI Sounds | UI Dialogues | When the player buy some special spell on the shop | SpecialSpell |  | DONE |  | Special spell updated
UI Sounds | UI Dialogues | When the player starts to play a new game | IntPT1 |  | DONE |  | In the ancient village of Eldoria, a darkness engulfed the forest of Krosa, and creatures filled with hatred and terror began to wander among the trees. After research, the high mages discovered they had released an ancient witch, imprisoned for poisoning nature with death and destruction.
UI Sounds | UI Dialogues | When the player starts to play a new game | IntPT2 |  | DONE |  | You have been chosen to combat the evil of Morgana, the profane, whose poison is killing Krosa through a dense, dark mist. The task is extremely dangerous, as the mist creates illusions and grotesque mutations in the forest's creatures. We hope you succeed, or we will have to find someone more competent.
UI Sounds | UI Dialogues | When the player get extra health on the shop | AsACat |  | DONE |  | As a cat you will now have more lives
UI Sounds | UI Dialogues | When the player dies and click in return | DiedQuickly |  | DONE |  | Oh, you died quickly huh noob, Apparently you didn't even click on our button about how to play.

## Enemies Features
Enemy | Speed
Werewolf | 3
Killer Pig | 2
Elkdemon | 1
Abomination | 3

## Project Milestones
Projects Steps | Start Date | End Date | Period of time | Features (What we need to deliver)
Prototype | 13/5/2024 | 2024-03-06 | 3 weeks
Alpha Version | 2024-03-06 | 17/06/2024 | 2 weeks
Beta Version | 17/06/2024 | 24/06/2024 | 1 week
Polishment | 24/06/2024 | 2024-01-07 | 1 week
1- Core System Working;
2- Basic UI elements working (Just enough for we see the game working);
3- A first version of the player character, one enemy and the map until fight agains the first enemies.
1- Basic movement's animations;
2- Different enemies mechanics;
3- Every simple enemy model implemented and also the items;
4- The game play sounds.
The complete game but working properly.
At this phase we will do a large playtest to identify some improvement points.
The final version

## Marketing Plan
Content | Kind | Theme | Description | Team Member Involved | Secondary Member Involved
Teaser #1 | Social Media Post | Project Introduction | Show the concept art being used on the primary GDD, explain a bit about the game concept and the game features. | Daril Camilo
Teaser #2 | Social Media Post | The Character | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Autumn McClinchey
Teaser #3 | Social Media Post | The Enemies | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Anna Victoria
Teaser #4 | Social Media Post | The Environment | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Autumn McClinchey |  | Daril Camilo | Public Relations
Teaser #5 | Social Media Post | The Boss | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Autumn McClinchey |  | Anna Victoria | Text Interview
Teaser #6 | Social Media Post | The Temples | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Autumn McClinchey |  | Renee Pollet | Podcast Interview
Teaser #7 | Social Media Post | The Spells | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Anna Victoria | Renee Pollet | Autumn McClinchey | Social Media Post
Teaser #8 | Social Media Post | The UI / UX | Moodboard, Inspiration, Sketches and a small text about the artist thoughts | Tierra Nguyen | Musse Hidru | Musse Hidru
Teaser #9 | Social Media Post | The Code | The Archtecture, References and the good practices | Renee Pollet | Musse Hidru | Tierra Nguyen

## Marketing Channels
Communication Channel | Kind | Specific Channel / Page / Group
Facebook | Social Media | Company's Page | Website | Facebook
Instagram | Social Media | Company's Page | Social Media | Instagram
Discord | Communication System | Calgary Game Developers Association | Podcast | Linked In
Discord | Communication System | Amir Satvat's Game Community | Youtube Channel | Discord
Discord | Communication System | Marcos Game Dev | Communication System | Reddit
Discord | Communication System | Game Dev Field Guide |  | Team Kraken Hunters

## OCS
Platform | Link
Facebook | https://www.facebook.com/TeamKrakenHunters
Instagram | https://www.instagram.com/teamkrakenhunters/
Linkedin | https://www.linkedin.com/company/team-kraken-hunters/
Website
Podcast
Youtube Channel
Reddit